## Coria Burndown Chart Template
SPRINT BURNDOWN CHART
| Backlog Category | User Stories / Bugs |  | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01
|  |  | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Project Step | Create a burndown chart | 4 | 2020-04-22: 4 |  | Legend
| Template | Create a login functionality | 3
| Template | Create more Tables | 1
| Template | Implement security protocol for SQL database appsettings.json file | 4
| Bug | Unable to create IW, JC, and MC button | 2
| Enhancement | Add MCN to Workload | 3 | bar: 2020-04-23
[16 empty] | = | Missing at Start
[16 empty] | = | Added to Sprint
[16 empty] | = | Projected Value
|  | Remaining Effort | 17 | 13 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
|  | Ideal Trend | 17 | 13.6 | 10.2 | 6.8 | 3.4 | 0 | -3.4 | -5.1 | -6.8 | -8.5 | -10.2 | Change the divisor to days of remaining work to
finish sprint. Ex., if 5 days of work, divide to 5.
Note on E5: Admin: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer. OMAF: Use this as a priority values. 1 is the lowest.
Note on R13: Coria: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on R14: Coria: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on R15: Coria: If you are only partway through a Sprint, but would like to project a completion or perform what-if analysis, use this formatting to indicate something is not yet final.