## Coria Burndown Chart Template
SPRINT BURNDOWN CHART
| Backlog Category | User Stories / Bugs |  | Jul 11th | Jul 12th | Jul 13th | Jul 14th | Jul 15th | Jul 18th | Jul 19th | Jul 20th | Jul 21st | Jul 22nd
|  |  | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Template | Create profile page for each user | 1 | [10 empty] | Legend
| Template | Create a login functionality | 3
| Template | Create more Tables | 1
| Template | Implement security protocol for SQL database appsettings.json file | 4
| Bug | Unable to create IW, JC, and MC button | 2
| Enhancement | Add a pie chart to Job Status | 1
| Enhancement | Use SportStore App "Add to cart" button when an inspector is ready to sign off MAFs. | 1
| Enhancement | Implement text messaging | 1 | [11 empty] | = | Missing at Start
[15 empty] | = | Added to Sprint
[15 empty] | = | Projected Value
|  | Remaining Effort | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
|  | Ideal Trend | 14 | 12.6 | 11.2 | 9.8 | 8.4 | 7 | 5.6 | 4.2 | 2.8 | 1.4 | -2.2204e-15
Note on E5: Admin: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer. OMAF: Use this as a priority values. 1 is the lowest.
Note on R13: Coria: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on R14: Coria: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on R15: Coria: If you are only partway through a Sprint, but would like to project a completion or perform what-if analysis, use this formatting to indicate something is not yet final.